## Activities
Activity Name | Type | Week | Responsible | Estimated Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 3
Feature Research | Requirements | 3 | Everyone | 6 | 6 | Done | Reseaching what people want | 0 | 0
Project Name | Design | 3 | Everyone | 0.5 | 0.25 | Done | Name of the App | 0.25 | 100
Software Requirements | Requirements | 3 | Tim | 1 | 1 | Done | Decide what software is needed | 0 | 0
GitHub Setup | Preparation | 3 | Everyone | 2 | 2 | Done | Create accounts and get access | 0 | 0
Java Learning | Preparation | 3 | Everyone | 10 | 10 | Done | Quick run through of Java for development | 0 | 0
Done
Done
Done
Done
Done
Done
Week 4
Plan/Create Features List | Preparation | 4 | Everyone | 1.5 | 1.5 | Done | Get a list of features for the app | 0 | 0
Research Social Media Integration | Preparation | 4 | Brandon | 2 |  | Ongoing | Research how to begin social media integration
Main Menu/General UI Design | Design | 4 | Everyone | 0.75 | 0.75 | Done | Design UI for main screen | 0 | 0
Create Use Cases for Features | Documentation | 4 | Everyone | 8 |  | Ongoing | Create use cases for features for Assignment 1
Design UI for Workout Plan Manager | Documentation | 4 | Alex | 2 |  | Ongoing | Design UI for workout plan manager
Design UI for Diet Management | Documentation | 4 | Trang | 2 |  | Ongoing | Design UI for diet management
Design UI for Progression Tracker | Documentation | 4 | Tim | 2 |  | Ongoing | Design UI for progression tracker
Design UI for Friends List | Documentation | 4 | Xinchi | 2 |  | Ongoing | Design UI for friends list
Design UI for GPS Running Tracker | Documentation | 4 | Chase | 2 |  | Ongoing | Design UI for gps running tracker
Design UI for Social Media Integration | Documentation | 4 | Brandon | 2 |  | Ongoing | Design UI for social media sharing
Week 5
Create Use Cases for Features | Documentation | 5 | Everyone | 8 | 8 | Done | Create use cases for features for Assignment 1 | 0 | 0
Design UI for Workout Plan Manager | Documentation | 5 | Alex | 2 |  | Ongoing | Design UI for workout plan manager
Design UI for Diet Management | Documentation | 5 | Trang | 2 |  | Ongoing | Design UI for diet management
Design UI for Progression Tracker | Documentation | 5 | Tim | 2 |  | Ongoing | Design UI for progression tracker
Design UI for Friends List | Documentation | 5 | Xinchi | 2 |  | Ongoing | Design UI for friends list
Design UI for GPS Running Tracker | Documentation | 5 | Chase | 2 |  | Ongoing | Design UI for gps running tracker
Design UI for Social Media Integration | Documentation | 5 | Brandon | 2 |  | Ongoing | Design UI for social media sharing
Download Andriod Studio Software | Development | 5 | Everyone | 2.5 |  | Ongoing | Get software installed to begin development
Review Information on Andriod Studio Tutorial Website | Preparation | 5 | Everyone | 8 |  | Ongoing | Get familiar with website to help begin development
Week 6
Design UI for Workout Plan Manager | Documentation | 6 | Alex | 2 | 0.3 | Done | Design UI for workout plan manager | 1.7 | 566.6667
Design UI for Diet Management | Documentation | 6 | Trang | 2 | 0.3 | Done | Design UI for diet management | 1.7 | 566.6667
Design UI for Progression Tracker | Documentation | 6 | Tim | 2 | 0.3 | Done | Design UI for progression tracker | 1.7 | 566.6667
Design UI for Friends List | Documentation | 6 | Xinchi | 2 | 0.3 | Done | Design UI for friends list | 1.7 | 566.6667
Design UI for GPS Running Tracker | Documentation | 6 | Chase | 2 | 0.3 | Done | Design UI for gps running tracker | 1.7 | 566.6667
Design UI for Social Media Integration | Documentation | 6 | Brandon | 2 | 0.3 | Done | Design UI for social media sharing | 1.7 | 566.6667
Download Andriod Studio Software | Development | 6 | Everyone | 2.5 | 3 | Done | Get software installed to begin development | -0.5 | 16.6667
Review Information on Andriod Studio Tutorial Website | Preparation | 6 | Everyone | 25 |  | Ongoing | Get familiar with website to help begin development
Week 7
Design UML Diagram for Project | Documentation | 7 | Brandon | 2 | 3 | Done | Design complete | -1 | 33.3333
Design UML Diagram for Project | Documentation | 7 | Tim | 2 | 3 | Done | Design complete | -1 | 33.3333
Design UML Diagram for Project | Documentation | 7 | Chase | 2 | 3 | Done | Design complete | -1 | 33.3333
Design UML Diagram for Project | Documentation | 7 | Trang | 2 | 3 | Done | Design complete | -1 | 33.3333
Design UML Diagram for Project | Documentation | 7 | Alex | 2 | 3 | Done | Design complete | -1 | 33.3333
Create UML Diagram for Database | Documentation | 7 | Chase | 1 | 1 | Done | Design complete | 0 | 0
User login functionality added to app | Development | 7 | Brandon | 3 |  | Ongoing | Implementation in progress
Design Logo and Choose team color | Design | 7 | Alex | 1 |  | Ongoing | Design in progress
Review Information on Andriod Studio Tutorial Website | Preparation | 7 | Everyone | 25 | 25 | Done | Everyone has looked at the tutorials
Done
Week 8
User login functionality added to app | Interfaces | 8 | Brandon | 3 |  | Ongoing | Need to set up to connect with Database
Design Logo and Choose team color | Design | 8 | Alex | 1 |  | Ongoing | Design in progress
Database setup | Development | 8 | Chase | 1 | 3 | Done | Database is now able to be connected to remotely | -2 | 66.6667
User profile Interface/Activity | Interfaces | 8 | Brandon | 1 |  | Ongoing | Relaying design to the actual app
Database setup | Development | 8 | Xingchi | 1 | 3 | Done | Database is now able to be connected to remotely
Database setup | Development | 8 | Trang | 1 | 3 | Done | Database is now able to be connected to remotely | -2 | 66.6667
Database setup | Development | 8 | Tim | 1 | 3 | Done | Database is now able to be connected to remotely | -2 | 66.6667
Create tables in Database | Development | 8 | Trang | 1 |  | Ongoing | Setting up tables to hold app data
Create tables in Database | Development | 8 | Tim | 1 |  | Ongoing | Setting up tables to hold app data
Week 9
Login funcitonality added to the app | Development | 9 | Brandon | 1 | 2 | Done | Screens are complete. But still need to check for user credentials and interact with database | -1 | 50
UI Complete for Statistics functionality | Development | 9 | Brandon | 1 | 2 | Done | Screens are implimented. But still need to pull data that is entered by user and have interaction with database | -1 | 50
UI Complete for Home screen | Development | 9 | Brandon | 1 | 1 | Done | Layout is implemented, need to refine to interact with database. Task will be created to get another member to implement database interaction. | 0 | 0
UI Complete for User profile screen | Development | 9 | Brandon | 1 | 1 | Done | Layout is implemented, need to refine to interact with database. Task will be created to get another member to implement database interaction. | 0 | 0
UI Complete for Diet screens | Development | 9 | Brandon | 1 | 2 | Done | Layout is implemented, need to refine to interact with database. Task will be created to get another member to implement database interaction. | -1 | 50
UI Complete for Workouts screens | Development | 9 | Brandon | 1 | 1 | Done | Layout is implemented, need to refine to interact with database. Task will be created to get another member to implement database interaction. | 0 | 0
UI Complete for Exercises screens | Development | 9 | Brandon | 1 | 2 | Done | Layout is implemented, need to refine to interact with database. Task will be created to get another member to implement database interaction. | -1 | 50
UI Complete for Friends List screens | Development | 9 | Brandon | 1 | 0.5 | Done | Layout is implemented, need to refine to interact with database. Task will be created to get another member to implement database interaction. | 0.5 | 100
Fixed bug for Logout not sending user to the Login screen | Development | 9 | Brandon | 1 | 2 | Done | Logout menu option now takes the user to login screen. | -1 | 50
Database Table Creation | Development | 9 | Tim | 2 | 2 | Done | Tables have been created to hold data. | 0 | 0
Database Table Creation | Development | 9 | Trang | 2 | 2 | Done | Tables have been created to hold data. | 0 | 0
Database Table Creation | Development | 9 | Chase | 2 | 2 | Done | Tables have been created to hold data. | 0 | 0
Design Logo and Choose team color | Design | 9 | Alex |  |  | Ongoing
Done
Week 10
Uploaded To Do list of items left to complete in Repository | Documentation | 10 | Brandon | 0.25 | 0.25 | Done | List of all remaining tasks for the project | -0.25 | 50
Design Logo and Choose team color | Design | 10 | Alex |  |  | Ongoing | Logo for login screen
Set up user login and registration to interact with database | Development | 10 | Brandon |  |  | Ongoing | Make sure user is able to register and have data saved in database
Database tables adjsutments | Development | 10 | Brandon |  |  | Ongoing | Adjusting on an as-needed basis
Database tables adjsutments | Development | 10 | Chase |  |  | Ongoing | Adjusting on an as-needed basis
Add default workouts to the Activities page | Development | 10 | Alex |  |  | Ongoing | Create default workouts to be added to every user's profile
Add default exercises to the Activities page | Development | 10 | Alex |  |  | Ongoing | Create default exercises to be added to every user's profile
Need to put an image on the Workouts pages | Development | 10 | Alex |  |  | Ongoing | Need images for workouts
Database tables adjsutments | Development | 10 | Tim |  |  | Ongoing | Adjusting on an as-needed basis
Done
Done
[6 empty] | Done |  | -4 | 50
Done
Done
Done
Week 11
Design Logo and Choose team color | Design | 11 | Alex |  |  | Ongoing | Logo for login screen
Set up user login and registration to interact with database | Development | 11 | Brandon | 4 | 8 | Done | Users are now unable to login without registering with an account | -4 | 50
Database tables adjsutments | Development | 11 | Brandon | 1 | 2 | Done | Adjustments have been made and discussed to accommodate for requirement updates on preloaded exercises | -1 | 50
Database tables adjsutments | Development | 11 | Chase | 0.25 | 0.5 | Ongoing | Adjustments have been made and discussed to accommodate for requirement updates on preloaded exercises
Add default workouts to the Activities page | Development | 11 | Brandon | 2 |  | Ongoing | Create default workouts to be added to every user's profile
Add default exercises to the Activities page | Development | 11 | Brandon | 1 | 0.5 | Done | Create default exercises to be added to every user's profile
Need to put an image on the Workouts pages | Development | 11 | Alex |  |  | Ongoing | Need images for workouts
Database tables adjsutments | Development | 11 | Tim | 0.25 | 0.5 | Ongoing | Adjustments have been made and discussed to accommodate for requirement updates on preloaded exercises
GPS Running Tracker feature | Development | 11 | Chase | 5 |  | Ongoing | Develop feature to allow users to track their runs and send data to the database
Done
Done
Done
Week 12
Design Logo and Choose team color | Design | 12 | Alex | 1 | 3 | Done | Logo for login screen | -2 | 66.6667
Fix bug with login and registration | Development | 12 | Brandon | 1 | 0.5 | Done | Meaningful messages display when correct and incorrect fields are entered
Activities Center - Workouts list | Development | 12 | Brandon | 3 | 5 | Done | When Activities Page is loaded, The user's workouts will display in a list view and are clickable | -2 | 40
Workout View | Development | 12 | Brandon | 3 | 4 | Done | When workout is selected from user's list of workouts, the workout view screen loads and populates all fields associated with that workout | -1 | 25
Edit Workout | Development | 12 | Brandon | 2 | 5 | Done | User is now able to edit a workout and save the changes. Workout view is loaded after save and populates updated information in the database | -3 | 60
UI Design improvements | Development | 12 | Brandon | 6 |  | Ongoing | Adding images and design improvements to the UI
Add default workouts to the Activities page | Development | 12 | Brandon | 2 |  | Ongoing | Create default workouts to be added to every user's profile
Store php scrips on non-local server | Development | 12 | Chase | 1 | 1 | Done | Scripts are now able to be stored on a remote server for access
GPS Running Tracker feature | Development | 12 | Chase | 5 |  | Ongoing | Develop feature to allow users to track their runs and send data to the database
Week 13
Activities Center - Workouts list | Development | 13 | Brandon | 1 | 1 | Done | Activites Center is complete. Shows workouts that the home user has created as well as viewing who follows the home user | 0 | 0
Add Workout | Development | 13 | Brandon | 1 | 1 | Done | Workouts now are able to be created by the user and correctly update all database tables accordingly. Delete functionality is also working the same way | 0 | 0
Settings Page | Development | 13 | Brandon | 1 | 0.25 | Done | Settings page allows the user to changs their username and password if permitted to do so | 0.75 | 300
Diet Stats | Development | 13 | Brandon | 1 | 4 | Done | Diet Stats now show correct information and clear data out every 24 hours
Workout Stats | Development | 13 | Brandon | 2 | 3 | Done | Workout stats correctly pull workouts that belong to the user and show how often each workout is performed compared to the others
Friends List | Development | 13 | Brandon | 2 | 2 | Done | Friends List page shows all users who are signed up with Workout With Friends. Users can search and request to follow users they like.
User's List Search | Development | 13 | Brandon | 1 | 5 | Done | Friends List is searchable and can be filtered based on quereys entered by the user in the search view box
Profile UI Design/Implementation | Development | 13 | Brandon | 2 | 4 | Done | UI for the user's profile is complete. Shows workouts, button to view followers, and shows user's information.
Unfollow/Follow User Functionality | Development | 13 | Brandon | 3 | 4 | Done | users can follow and unfollow users. Database records are updtated with each instance
Home Page UI | Development | 13 | Brandon | 2 | 4 | Done | Home screen has images for navigation with a help section on how to start | -2 | 50
Meal Submission Page | Development | 13 | Brandon | 1 | 4 | Done | Meals are now able to be submitted and database tables will be updated accordingly | -3 | 75
Create Workout | Development | 13 | Brandon | 3 | 4 | Done | User can now create a workout and it will populate in their workout list | -1 | 25
Record Meal | Development | 13 | Brandon | 2 | 4 | Done | Users can now record a meal they have eaten and it will update stats for diet | -2 | 50
Workout Calorie Calculations | Development | 13 | Brandon | 3 | 3 | Done | Workouts will calculate correct amount of calories burned based on weight, exercises, and time spent on each exercise | 0 | 0
Navigation Header | Development | 13 | Brandon | 3 | 1 | Done | Minor adjustments were made to make navigation options more clear to the user. Easier to understand wording. | 2 | 200
UI Design | Development | 13 | Brandon | 3 | 5 | Done | UI for app is complete. | -2 | 40
GPS Running Tracker feature | Development | 12 | Chase | 5 |  | Ongoing | Develop feature to allow users to track their runs and send data to the database
Note on C1: swami: This is useful for generating subtotals and reports
Note on D1: SE: The person responsible for ensuring completion, not necessarily all the people doing it
Note on H1: swami: Insert your own comments
Note on I1: SE: This field is updated automatically

## SummaryData
Note: All data on this sheet updated automatically
Item |  | Week |  | Total Estimation Error % | Count | Average Estimation Error %
Criteria
Week | Week | Week | Week | Week | Week | Week | Week | Week | Week
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
EstimationError
Week1 |  | 1 |  | 0 | 0 | 0
Week2 |  | 2 |  | 0 | 0 | 0
Week3 |  | 3 |  | 100 | 5 | 20
Week4 |  | 4 |  | 0 | 2 | 0
Week5 |  | 5 |  | 0 | 1 | 0
Week6 |  | 6 |  | 3416.6667 | 7 | 488.0952
Week7 |  | 7 |  | 166.6667 | 6 | 27.7778
Week8 |  | 8 |  | 200 | 3 | 66.6667
Week9 |  | 9 |  | 350 | 12 | 29.1667
Week10 |  | 10 |  | 50 | 1 | 50
Activity |  |  |  |  | Actual Effort
Requirements |  |  |  |  | 7
Design |  |  |  |  | 4
Development |  |  |  |  | 110.75
Testing |  |  |  |  | 0
Interfaces |  |  |  |  | 0
Documentation |  |  |  |  | 26.05
Coordination |  |  |  |  | 0
Preparation |  |  |  |  | 38.5
Delivery |  |  |  |  | 0
Criteria
Type | Type | Type | Type | Type | Type | Type | Type | Type
Requirements | Design | Development | Testing | Interfaces | Documentation | Coordination | Preparation | Delivery
EstimationError |  | Total | Count | Average
Requirements |  | 0 | 2 | 0
Design |  | 166.6667 | 3 | 55.5556
Development |  | 1531.6667 | 31 | 49.4086
Testing |  | 0 | 0 | 0
Interfaces |  | 0 | 0 | 0
Documentation |  | 3616.6667 | 14 | 258.3333
Coordination |  | 0 | 0 | 0
Preparation |  | 0 | 3 | 0
Delivery |  | 0 | 0 | 0
Week-wise-Effort
Week1 |  | 1 |  |  | 0
Week2 |  | 2 |  |  | 0
Week3 |  | 3 |  |  | 19.25
Week4 |  | 4 |  |  | 2.25
Week5 |  | 5 |  |  | 8
Week6 |  | 6 |  |  | 4.8
Week7 |  | 7 |  |  | 41
Week8 |  | 8 |  |  | 12
Week9 |  | 9 |  |  | 19.5
Week10 |  | 10 |  |  | 0.25
Total effort |  |  |  |  | 107.05

## Reports
The charts here update automatically

## Instructions
Using the activity tracker
At the end of each week, update the status of all activities completed during the week
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
After each release, look at the "reports" section to see charts of how much time has been spent so far, and what activities it has been spent on
Use the charts and data to identify needs for improvement